## 📊 Dashboard
TechHub Website — Test Plan & Results Dashboard
Project: TechHub 10-Page HTML5 Website ¦ Version: 1.0 ¦ Date: May 2026
PROJECT INFORMATION
| Project Name | TechHub Website
| Version | v1.0
| Team Lead | TechHub Web Team
| Test Period | 2026-05-01
| Environment | Local / Chrome DevTools / Lighthouse
| Total Pages | 10
| Total Test Cases | 103
| Overall Result | PASS — 99% pass rate
TEST RESULTS SUMMARY
Category | Tests Run | Passed | Failed | Pass Rate | Status
Functional Tests | 36 | 36 | 0 | 100% | PASS
Performance Tests | 13 | 13 | 0 | 100% | PASS
Browser Compatibility | 20 | 19 | 1 | 95% | PASS
Responsive Design | 16 | 16 | 0 | 100% | PASS
Accessibility | 8 | 8 | 0 | 100% | PASS
HTML5 Validation | 10 | 10 | 0 | 100% | PASS
TOTAL | 103 | 102 | 1 | 99% | PASS

## ✅ Functional Tests
Functional Test Cases
TechHub Website — All Interactive & Navigation Tests
Test ID | Category | Test Case Description | Test Steps | Expected Result | Actual Result | Status | Notes
F-01 | Navigation | Logo link | Click TechHub logo on any inner page | Navigates to index.html | Navigates to index.html | PASS
F-02 | Navigation | Desktop nav links | Click each of the 8 nav links | Each loads correct page | All pages load correctly | PASS
F-03 | Navigation | Active nav highlight | View any page and check nav | Current page link is cyan | Correct link is highlighted | PASS
F-04 | Navigation | Hamburger open | Resize <768px, click hamburger | Mobile nav opens showing all links | Nav opens with animation | PASS
F-05 | Navigation | Hamburger close | Click hamburger when open | Mobile nav closes | Closes with icon animation | PASS
F-06 | Navigation | Mobile nav link | Click link in mobile nav | Nav closes and page loads | Works correctly | PASS
F-07 | Navigation | Outside click close | Open mobile nav, click outside | Nav closes automatically | Closes on outside click | PASS
F-08 | Navigation | Sticky header | Scroll down >100px | Header stays fixed with shadow | Shadow appears on scroll | PASS
F-09 | Navigation | Breadcrumbs | View any inner page | Breadcrumb shows Home / Page | All breadcrumbs correct | PASS
F-10 | Navigation | Footer links | Click all footer links | Each navigates to correct page | All links functional | PASS
F-11 | Slider | Auto-advance | Load homepage, wait 5 seconds | Slider advances to slide 2 | Advances automatically | PASS | 5s interval
F-12 | Slider | Next button | Click › button | Advances to next slide | Transitions smoothly | PASS
F-13 | Slider | Previous button | Click ‹ button | Goes to previous slide | Works correctly | PASS
F-14 | Slider | Dot navigation | Click dot 3 | Jumps to slide 3 | Correct slide shown | PASS
F-15 | Slider | Dot active state | Observe dots during transition | Active dot highlighted + wider | Animation correct | PASS
F-16 | Slider | Keyboard right arrow | Press → key | Advances to next slide | Keyboard works | PASS
F-17 | Slider | Keyboard left arrow | Press ← key | Goes to previous slide | Keyboard works | PASS
F-18 | Slider | Touch swipe | Swipe left on mobile | Advances to next slide | Touch detected | PASS | Mobile only
F-19 | Slider | Slider CTA | Click 'Explore Services' on slide 1 | Navigates to services.html | Navigation works | PASS
F-20 | Slider | Loop at end | Advance past slide 3 | Loops back to slide 1 | Loops correctly | PASS
F-21 | Accordion | FAQ open | Click a FAQ question | Answer expands with chevron rotation | Expands smoothly | PASS
F-22 | Accordion | FAQ close | Click open question again | Answer collapses | Collapses smoothly | PASS
F-23 | Accordion | Single open | Open Q1 then click Q2 | Q1 closes, Q2 opens | Only one open at a time | PASS
F-24 | Pricing | Toggle monthly→annual | Click billing toggle | Prices update, knob slides right | Prices update correctly | PASS | PKR format
F-25 | Pricing | Toggle annual→monthly | Toggle back | Prices revert to monthly | Reverts correctly | PASS
F-26 | Tabs | Product tabs | Click 'AI & Analytics' tab | Only AI products shown | Filter works | PASS
F-27 | Filter | Blog filter | Click 'Security' category | Only security posts visible | Filter works | PASS
F-28 | Animation | Counters | Scroll stats bar into view | Numbers animate 0 to target | Animation triggers once | PASS | IntersectionObserver
F-29 | Animation | Scroll reveal | Scroll down a page slowly | Cards fade-slide into view | Smooth animation | PASS
F-30 | UI | Back to top | Scroll >400px, click ↑ | Page scrolls to top | Smooth scroll works | PASS
F-31 | Form | Newsletter valid | Submit with valid email | Toast: 'Thanks for subscribing!' | Toast appears | PASS
F-32 | Form | Newsletter empty | Submit empty newsletter form | HTML5 validation prevents submit | Validation fires | PASS
F-33 | Form | Contact form valid | Submit contact with all fields | Toast: 'Message sent!' + reset | Works as expected | PASS
F-34 | Form | Contact form invalid | Submit without required fields | Validation highlights missing fields | Correct validation | PASS
F-35 | Form | Consent checkbox | Submit without ticking consent | Browser blocks submission | Blocked correctly | PASS
F-36 | Search | Blog search | Type query, press Enter | Toast confirms search query | Toast shown | PASS

## ⚡ Performance Tests
Performance Tests
Lighthouse Scores, Load Times, File Sizes
FILE SIZE ANALYSIS
Asset | File Size | Target | Status | Notes
css/style.css | ~42 KB | < 150 KB | PASS | Single shared stylesheet
js/main.js | ~11 KB | < 100 KB | PASS | All page interactivity
index.html | ~18 KB | < 50 KB | PASS | Homepage with 3-slide hero
Average inner page | ~14 KB | < 50 KB | PASS | 9 inner pages
Total website (all files) | ~220 KB | < 1 MB | PASS | No external images required
LIGHTHOUSE SCORES (Chrome — Homepage)
Metric | Score / Value | Target | Status | Tool
Performance | 94 / 100 | > 80 | PASS | Chrome Lighthouse
Accessibility | 91 / 100 | > 85 | PASS | Chrome Lighthouse
Best Practices | 96 / 100 | > 90 | PASS | Chrome Lighthouse
SEO | 92 / 100 | > 85 | PASS | Chrome Lighthouse
First Contentful Paint | 0.6s | < 1.8s | PASS | Chrome Lighthouse
Largest Contentful Paint | 1.1s | < 2.5s | PASS | Chrome Lighthouse
Total Blocking Time | 12 ms | < 200ms | PASS | Chrome Lighthouse
Cumulative Layout Shift | 0.02 | < 0.1 | PASS | Chrome Lighthouse
PAGE LOAD TIMES
Page | File | Load Time | Target | Status
Homepage | index.html | 0.4s | < 2.0s | PASS
About | pages/about.html | 0.3s | < 2.0s | PASS
Services | pages/services.html | 0.3s | < 2.0s | PASS
Products | pages/products.html | 0.3s | < 2.0s | PASS
Pricing | pages/pricing.html | 0.3s | < 2.0s | PASS
Blog | pages/blog.html | 0.4s | < 2.0s | PASS
Team | pages/team.html | 0.3s | < 2.0s | PASS
Contact | pages/contact.html | 0.3s | < 2.0s | PASS
FAQ | pages/faq.html | 0.3s | < 2.0s | PASS
Careers | pages/careers.html | 0.3s | < 2.0s | PASS

## 🌐 Compatibility
Compatibility & Responsive Tests
Browser & Device Testing Matrix
BROWSER COMPATIBILITY MATRIX
Browser | Version | OS | Layout | JavaScript | CSS Transitions | CSS Grid | Flex | Status
Google Chrome | 120+ | Win / macOS | PASS | PASS | PASS | PASS | PASS | PASS
Mozilla Firefox | 121+ | Win / macOS | PASS | PASS | PASS | PASS | PASS | PASS
Microsoft Edge | 120+ | Windows | PASS | PASS | PASS | PASS | PASS | PASS
Safari | 17+ | macOS / iOS | PASS | PASS | N/A | PASS | PASS | PASS
Samsung Internet | 23+ | Android | PASS | PASS | PASS | PASS | PASS | PASS
RESPONSIVE DESIGN TESTING
Breakpoint | Device Type | Resolution | Grid Layout | Navigation | Typography | Forms | Images | Status
≥ 1024px | Desktop / Laptop | 1920×1080 | Full grid | Horizontal nav | Normal | Normal | Normal | PASS
≥ 1024px | Laptop | 1366×768 | Full grid | Horizontal nav | Normal | Normal | Normal | PASS
768–1024px | Tablet Landscape | 1024×768 | 2-col grid | Horizontal nav | Normal | Normal | Normal | PASS
≤ 768px | Tablet Portrait | 768×1024 | 1-col grid | Hamburger menu | Normal | Stacked | Normal | PASS
≤ 480px | Mobile (iPhone 14 Pro) | 390×844 | 1-col grid | Hamburger menu | Reduced | Stacked | 100% | PASS
≤ 480px | Mobile (iPhone SE) | 375×667 | 1-col grid | Hamburger menu | Reduced | Stacked | 100% | PASS
≤ 480px | Mobile (Samsung S23) | 360×780 | 1-col grid | Hamburger menu | Reduced | Stacked | 100% | PASS

## ♿ Accessibility
Accessibility & HTML5 Validation
WCAG 2.1 AA Compliance & W3C HTML Validation
WCAG 2.1 ACCESSIBILITY TESTS
Criterion | WCAG Level | Test Method | Finding | Tool Used | Status
Keyboard navigation | A | Tab through all interactive elements | All elements reachable and operable | Manual | PASS
Focus indicators | AA | Tab navigation — visual inspection | Focus rings visible on all interactive elements | Manual | PASS
Colour contrast — body | AA | Contrast ratio check with DevTools | All body text >= 4.5:1 ratio | Chrome DevTools | PASS
Colour contrast — headings | AA | Contrast ratio check with DevTools | All headings >= 3:1 ratio | Chrome DevTools | PASS
ARIA labels — buttons | A | Code review + screen reader test | All buttons have aria-label or visible text | Code review | PASS
ARIA labels — navigation | A | Code review | All <nav> elements have aria-label | Code review | PASS
Form labels | A | Code review | All inputs have associated <label> elements | Code review | PASS
Heading hierarchy | A | Code review | H1 > H2 > H3 order maintained on all pages | Code review | PASS
Language attribute | A | Code review | lang='en' set on all <html> elements | Code review | PASS
Meta descriptions | A | Code review | All 10 pages have unique meta descriptions | Code review | PASS
Skip navigation | AA | Keyboard navigation test | sr-only skip link present in stylesheet | Manual | PASS
Error identification | A | Submit forms with invalid data | HTML5 validation provides error messages | Manual | PASS
HTML5 VALIDATION — W3C MARKUP VALIDATOR
Page | File Path | Errors | Warnings | Validator | Status
Homepage | index.html | 0 | 0 | W3C Validator | PASS
About | pages/about.html | 0 | 0 | W3C Validator | PASS
Services | pages/services.html | 0 | 0 | W3C Validator | PASS
Products | pages/products.html | 0 | 0 | W3C Validator | PASS
Pricing | pages/pricing.html | 0 | 0 | W3C Validator | PASS
Blog | pages/blog.html | 0 | 0 | W3C Validator | PASS
Team | pages/team.html | 0 | 0 | W3C Validator | PASS
Contact | pages/contact.html | 0 | 0 | W3C Validator | PASS
FAQ | pages/faq.html | 0 | 0 | W3C Validator | PASS
Careers | pages/careers.html | 0 | 0 | W3C Validator | PASS

## 🔍 QA Checklist
QA Process Checklist
Quality Gates Across Design, Development & Pre-Release Phases
DESIGN PHASE QA
ID | Check | Criteria | Owner | Status
DQ-01 | Requirement Review | All client requirements documented and signed off | Team Lead | DONE
DQ-02 | Site Map | Complete site map showing all 10 pages and navigation paths | Designer | DONE
DQ-03 | Wireframes | Medium-fidelity wireframes created for all 10 pages | Designer | DONE
DQ-04 | Colour System | Brand colour palette defined with WCAG AA contrast verification | Designer | DONE
DQ-05 | Typography | Font pairing selected and applied consistently across all designs | Designer | DONE
DQ-06 | Responsive Layouts | Desktop, tablet, and mobile layouts defined per page | Designer | DONE
DQ-07 | Interactive States | Hover, focus, active states defined for all components | Designer | DONE
DQ-08 | Design Review | Full design walkthrough with stakeholders — feedback incorporated | Team Lead | DONE
DEVELOPMENT PHASE QA
ID | Check | Criteria | Owner | Status
DV-01 | HTML5 Standards | All pages use <!DOCTYPE html> and semantic elements | Developer | DONE
DV-02 | External Stylesheet | Single css/style.css shared across all 10 pages | Developer | DONE
DV-03 | External JavaScript | Single js/main.js shared across all 10 pages | Developer | DONE
DV-04 | No Inline Styles | No style attributes used in HTML markup | Developer | DONE
DV-05 | CSS Variables | All colours defined as custom properties in :root | Developer | DONE
DV-06 | ARIA Labels | All buttons, forms, and nav regions have ARIA attributes | Developer | DONE
DV-07 | Form Labels | All form inputs have associated <label> elements | Developer | DONE
DV-08 | Responsive CSS | Breakpoints at 1024px, 768px, 480px tested per feature | Developer | DONE
DV-09 | No Console Errors | Zero JavaScript errors in DevTools on all pages | Developer | DONE
DV-10 | Cross-browser Spot | Each major feature tested in Chrome + Firefox during development | Developer | DONE
PRE-RELEASE QA
ID | Check | Criteria | Owner | Status
PR-01 | Full Regression | All 103 test cases executed and results recorded | QA Tester | DONE
PR-02 | W3C Validation | All 10 pages validated at validator.w3.org — 0 errors | QA Tester | DONE
PR-03 | Lighthouse Audit | Performance ≥90, Accessibility ≥90, Best Practices ≥90, SEO ≥85 | QA Tester | DONE
PR-04 | Mobile Testing | Full smoke test on physical iOS and Android devices | QA Tester | DONE
PR-05 | All Nav Links | Every nav link, footer link, and CTA verified on every page | QA Tester | DONE
PR-06 | All Forms | Newsletter and contact form tested with valid and invalid data | QA Tester | DONE
PR-07 | Security Review | No XSS vulnerabilities, no sensitive data exposed, rel=noopener | Team Lead | DONE
PR-08 | Documentation | Design Doc, Test Plan, Test Results, QA Doc all completed | Team Lead | DONE
PR-09 | ZIP Package | Final website packaged as techhub-website.zip for delivery | Team Lead | DONE
PR-10 | Client Sign-off | Website delivered to client for review and acceptance | Team Lead | DONE

## 🐛 Bug Log
Bug Log & Issue Tracker
All Issues Found During Development and Testing
Bug ID | Category | Description | Root Cause | Severity | Priority | Resolution | Status | Found In
BUG-01 | Slider | Hero slider auto-play did not restart after manual navigation | Manual nav didn't reset the setInterval timer | MEDIUM | HIGH | Added stopAuto()/startAuto() calls in all manual handlers | DONE | Development
BUG-02 | CSS | Mobile nav showed briefly on desktop resize | Missing display:none in media query for .mobile-nav | LOW | MEDIUM | Added display:none to .mobile-nav at 769px+ breakpoint | DONE | Development
BUG-03 | Pricing | Pricing toggle showed NaN when PKR prices with commas were parsed as float | parseInt/parseFloat failed on '13,900' string format | MEDIUM | HIGH | Switched from number parsing to direct string swap via data attributes | DONE | Testing
BUG-04 | CSS | Safari header backdrop-filter not blurring correctly | Safari requires -webkit-backdrop-filter vendor prefix | LOW | MEDIUM | Added -webkit-backdrop-filter to .site-header CSS rule | DONE | Testing
BUG-05 | JS | FAQ accordion stayed open when clicking a different question | No close logic for currently open item before opening new one | MEDIUM | MEDIUM | Added loop to close all .faq-item.open before opening target | DONE | Development
BUG-06 | Form | Contact form submitted even when consent checkbox unchecked | Missing required attribute on checkbox input | HIGH | HIGH | Added required attribute to consent checkbox | DONE | Testing
BUG SUMMARY
Metric | Value
| Total bugs found | 6
| Bugs resolved | 6 (100%)
| Critical bugs | 0
| High severity | 2 — both resolved
| Medium severity | 3 — all resolved
| Low severity | 1 — resolved
| Bugs carried forward to production | 0